## Needham Activities Tracker FY20
SSA (Hidden) | Label (Hidden) | Objectives | Description (pre-filled) | Custom Activity | This objective was selected due to | Racial Equity Consideration | Performance Standards Topic Area | Environmental Health Subcategory (if applicable) | Lead Contact | Is This Activity Related to the RE Consideration? | Staff Lead | Support Staff | Start Date | End Date | T1 Status | Completion Status T1 | T1 Progress Notes | T2 Status | T2 Completion Status | T2 Progress Notes | T3 Status | T3 Completion Status | T3 Progress Notes | At Risk
Charles River Public Health District | Town of Needham | Town of Needham | Last Reviewed: [Date] | [5 empty] | Kerry Dunnell | [5 empty] | Incomplete |  |  | Incomplete |  |  | Incomplete
Charles River Public Health District | Reporting | Reporting | R1: Review and update each sheet per reporting period | [5 empty] | Jessica Ferland | [6 empty] | Incomplete |  |  | Incomplete |  |  | Incomplete
Charles River Public Health District | Reporting |  | Individual Payments
Charles River Public Health District | Reporting |  | Staffing Chart
Charles River Public Health District | Reporting |  | Activities Tracker
Charles River Public Health District | Reporting |  | SSA Summary
Charles River Public Health District | Grant Administration | Grant Administration | PHE Grant Requirement 1: Grant Administration: Complete/perform all PHE Grant Program contractual requirements for the upcoming fiscal year
Charles River Public Health District | Grant Administration |  | Attend monthly PHE Grantee meetings – ensure attendance of lead municipality and Shared Services Coordinator (SSC), or a designated alternate. | [7 empty] | Kerry Dunnell | Sam Menard | 2024-07-01 | 2025-06-30 | Complete |  | Staff attend all meetings, notes are taken and shared if any staff member is unable to attend.
Charles River Public Health District | Grant Administration |  | Submit a list of Participating Municipalities to Program Coordinator by July 31st and notify Program Coordinator within 30 calendar days of a change in Participating Municipalities. | [7 empty] | Administrative Specialist | Kerry Dunnell | 2024-07-15 | 2025-07-31 | Complete
Charles River Public Health District | Grant Administration |  | Maintain Letters of Commitment (LOC) from all Participating Municipalities in the SSA. | [7 empty] | Administrative Specialist | Kerry Dunnell | 2024-07-01 | 2025-06-30 | Complete
Charles River Public Health District | Grant Administration |  | Complete and submit PHE triannual reports in collaboration with your Shared Services Coordinator and all municipalities within the SSA. | [7 empty] | Kerry Dunnell | Jen Casey | 2024-07-01 | 2025-06-30 | Complete
Charles River Public Health District | Grant Administration |  | Governing bodies established through the Intermunicipal Agreement (IMA), shall meet a minimum of once per quarter. | [7 empty] | Kerry Dunnell | Sam Menard | 2024-07-01 | 2025-06-30 | Complete |  | Charles River Public Health District meets monthly, alternating between in person & virtual meetings.
Charles River Public Health District | Grant Administration |  | Send annual notification to all Participating Municipalities no later than October 31st of each grant year. Such notification shall be substantially consistent with Attachment 1 of the PHE Engagement Scope in terms of required language and addressee list. Proof of notification shall be submitted to Program Coordinator no later than November 15th of each fiscal year. | [7 empty] | Kerry Dunnell | Adminstrative Specialist | 2024-07-15 | 2024-11-15 | Complete
Charles River Public Health District | Grant Administration |  | Ensure that all Participating Municipalities maintain 100% continuous MAVEN coverage which means that each Participating Municipality has an active, designated MAVEN user and back-up user. | [7 empty] | Regional Public Health Nurse | Sam Menard | 2024-08-01 | 2024-09-30 | Complete |  | Program manager confirms monthly with each community. Regional Public Health nurse will assume this responsibillity during TriTerm 2. All communities currently have 100% continuous coverage.
Charles River Public Health District | Grant Administration |  | Complete the biannual supplemental reporting survey (T2 and T3) | [7 empty] | Kerry Dunnell |  | 2024-11-01 | 2025-06-30 | Not Started |  | To be completed in Trimesters 2 & 3
Charles River Public Health District | Governance | Governance | PHE Grant Requirement 2: Governance: Execute and maintain IMA or equivalent
| Governance |  | If you haven’t already done so, Complete the Technical Assistance Request Form and select “IMA development” | [7 empty] | Kerry Dunnell | 10/1/2023 | 2023-10-01 |  | Complete
| Governance |  | Working with Massachusetts Association of Health Boards (MAHB), draft IMA in accordance with PHE Engagement Scope. | [7 empty] | Kerry Dunnell | 10/15/2023 | 2023-10-15 |  | Complete
| Governance |  | Circulate draft to Participating Municipalities and schedule a meeting to review and discuss. | [7 empty] | Kerry Dunnell | 1/1/2024 | 2024-04-30 |  | Complete
| Governance |  | Working with MAHB, incorporate edits and revisions as needed. | [7 empty] | Kerry Dunnell | 1/1/2024 | 2024-03-31 |  | Complete
| Governance |  | Request legal review by host municipality and subsequently legal review by Participating Municipalities in consultation with MAHB. | [7 empty] | Kerry Dunnell | 1/5/2024 | 2024-05-01 |  | Complete
| Governance |  | Schedule Board of Health and Select Board meetings as necessary to approve and execute final version of IMA. Provide IMA in advance of meetings and ensure adequate representation at meeting to answer questions. | [7 empty] | Kerry Dunnell | 7/15/2024 | 2024-08-31 |  | Complete
| Governance |  | Submit a fully executed IMA to Program Coordinator no later than October 31, 2024 | [7 empty] | Kerry Dunnell | 9/1/2024 | 2024-10-31 |  | Complete
Charles River Public Health District | FPHS Review | FPHS Review | PHE Grant Requirement 3: FPHS Review: Participate in trainings, a capacity and expertise review (SSA-level), and cost reporting related to the Foundational Public Health Services (FPHS).
Charles River Public Health District | FPHS Review |  | FPHS Checklist
Charles River Public Health District | FPHS Review |  | Attend Foundational Public Health Services (FPHS) Framework review trainings and technical assistance meetings, and gather necessary documents (e.g., municipal budgets). | [7 empty] | Kerry Dunnell | Sam Menard | 2024-11-01 | 2025-06-30 | Not Started
Charles River Public Health District | FPHS Review |  | Have your Shared Services Coordinator facilitate discussions with your SSA about capacity and expertise within the FPHS Foundational Areas and Foundational Capabilities to prepare for the capacity and expertise SSA-level review and cost reporting. | [7 empty] | Kerry Dunnell | Administrative Specialist | 2024-09-01 | 2025-06-30 | In Progress |  | Program manager has introduced topic of Foundational Public Health services and provided graphics and infromation sources. Addittionally, the Charles River collaborative engaged a consultant to conduct a fee cost study for existing services. These activities provide some preparation for the work of the upcoming FPHS assessment.
Charles River Public Health District | FPHS Review |  | Complete the FPHS Shared Services Review collaboratively with your SSA (early 2025). | [7 empty] | Kerry Dunnell | Sam Menard | 2024-10-01 | 2025-06-30 | Not Started
Charles River Public Health District | Sustainability | Sustainability 1 | 5 - Inventory Management: Establish an inventory management system to streamline procurement processes and accurately monitor all purchases
| Sustainability |  | Develop an SOP and/or implemenent a transparent tracking mechanism for inventory management related to the PHE Grant Program related purchases. | [7 empty] | Sam Menard | Kerry Dunnell | 2024-07-01 | 2025-02-28 | In Progress |  | Charles River staff have developed an inventory spreadsheet for all purchases and a checklist and preliminary procedure for quarterly inventory checks. Items above a dollar value of $100 will have bar codes affixed to enable identification and tracking. This inventory system will be tested and demonstrated to the Advisory Board in TriTerm 2.
| Sustainability |  | Itemize all purchases made by the SSA purchases, ensuring comprehensive documentation of procurement transactions. | [7 empty] | Sam Menard | Adminstrative Specialist | 2024-07-01 | 2024-07-31 | Complete |  | All purchases are made centrally by our adminstrative coordinator. Each purchase is itemized and details are used for the inventory mechanism.
| Sustainability |  | Train staff members on the newly established inventory management procedures. | [7 empty] | Sam Menard | Kerry Dunnell | 2025-01-01 | 2025-02-28 | Not Started |  | Training will occur during Triterm 2, after system is tested.
| Sustainability |  | Implement quarterly audits to refine the process, maintain accuracy, and identify any discrepancies. | [7 empty] | Sam Menard | Kerry Dunnell | 2025-01-01 | 2025-06-30 | Not Started |  | System includes a quarterly audit checklist and process. Work with this will be ongoing.
Charles River Public Health District | Sustainability | Sustainability 2 | 2 -Strategic Planning: Develop a shared vision to inform future work
Charles River Public Health District | Sustainability |  | Facilitate strategic planning workshops to identify service gaps, resource constraints, ensure SSA sustainability, and opportunities for collaboration among SSA municipalities. | [7 empty] | Kerry Dunnell | Administrative Specialist | 2024-12-01 | 2025-06-30 | Not Started |  | A Request for Quotes was developed for a strategic planning proposal. Vendors to be identified in November/early December 2024.
Charles River Public Health District | Sustainability |  | Develop a strategic vision and mission statement that aligns with the goals of the SSA and reflects the collective interests of all municipalities. | [7 empty] | Kerry Dunnell | Administrative Specialist | 2024-12-01 | 2025-06-30 | Not Started |  | This is part of the scope of work described in the RFQ
Charles River Public Health District | Sustainability |  | Present findings of strategic planning process to each community board of health. | TRUE | [6 empty] | Kerry Dunnell | Regional Environmental Health Inspector | 2025-03-01 | 2025-06-30 | Not Started |  | Once complete, results will be presented to each Board of Health
Charles River Public Health District | Sustainability |  | Evaluate existing contracted services and identify opportunities for merging (combining similar contracts) or expansion (expanding existing contracts to serve additional municipalities) within the SSA. | [7 empty] | Regional Environmental Health Inspector | Kerry Dunnell | 2024-10-01 | 2025-02-28 | In Progress |  | Regional Health inspector is including this information request as part of the Self-Assessment work being done by each community.
Charles River Public Health District | Performance Standards | Performance Standards 1 | 1 - Enhance staff capacity to effectively meet mandated inspectional requirements and enforce regulations, in alignment with the Performance Standards for Local Public Health |  | CART Assessment
Charles River Public Health District | Performance Standards | Performance Standards Topic Area | Environmental Health |  |  |  | Environmental Health
Charles River Public Health District | Performance Standards | Performance Standards Racial Equity Consideration | Workforce Diversity: create a work culture of diversity, equity, inclusion, and belonging, that values different viewpoints and lived experiences to improve employee satisfaction & retention |  |  | Workforce Diversity: create a work culture of diversity, equity, inclusion, and belonging, that values different viewpoints and lived experiences to improve employee satisfaction & retention
Charles River Public Health District | Performance Standards |  | Have all member municipalities complete the Self-Assessment for updated staffing needs. | [7 empty] | Regional Environmental Health Inspector | Administrative Specialist | 2024-10-01 | 2024-11-30 | In Progress |  | Self Assessments should be complete early in TriTerm 2.
Charles River Public Health District | Performance Standards |  | Create an SOP for how member municipalities request inspectional support. | [7 empty] | Regional Environmental Health Inspector | Sam Menard | 2024-10-01 | 2025-02-28 | In Progress |  | We are continuing to encourage communities to reach out on demand for support. Staff have discussed creating a procedure, yet want to avoid creating barriers to engagement with communities.
Charles River Public Health District | Performance Standards |  | Create a system for managing and supervising staff that offers clear guidance on job responsibilities, mechanisms for support, and mentoring. Guidance should also include ways to handle conflicts in the SSA. | [7 empty] | Kerry Dunnell | Sam Menard | 2024-07-01 | 2025-06-30 | In Progress |  | Shared services staff are all employees of Town of Needham and supervised internally. Agreements as to what services are being provided are made with each community based upon requests.
Charles River Public Health District | Performance Standards |  | Create an SOP for hiring. This should include procedures for securing approval at both the SSA and municipal levels, drafting and approving job descriptions, posting mechanics, selecting final candidates, salary expectations, incorporating workforce regulations, addressing future education and training needs, and ensuring fair and equitable hiring practices. | [7 empty] | Sam Menard | Kerry Dunnell | 2024-07-01 | 2024-02-28 | In Progress |  | Staff have been using and updating hiring and onboarding process tools. Final tools projected to be complete end of February 2025.
Charles River Public Health District | Performance Standards |  | Carry out the hiring plan, making sure to follow the set timelines, procedures, budget limits, while also ensuring representative diversity. | [6 empty] | TRUE | Sam Menard | Kerry Dunnell | 2024-07-01 | 2025-06-30 | In Progress |  | Charles River has developed a hiring and on boarding process and continually reviews and adjusts those based upon position as well as upon reflection and feedback from Town of Needham Human Resources, staff, and Advisory Board members. Town of Needham hiring system enables deidentifed review of all applications - striking name, employers, schools, etc. If a candidate is deemed potentially qualified, then their information can be 'unmasked'. This practice enables a 'blind review.'
Charles River Public Health District | Performance Standards | Performance Standards 2 | 4 - Disease Control and Prevention: Ensure adherence to infectious disease case investigation requirements, while enhancing staff training, capacity, and quality improvement initiatives |  | CART Assessment
Charles River Public Health District | Performance Standards | Performance Standards Topic Area | Disease Control and Prevention |  |  |  | Disease Control and Prevention
Charles River Public Health District | Performance Standards | Performance Standards Racial Equity Consideration | CLAS Standards: advancing health & racial equity, through data collection, and diversifying workforce to represent community; ensuring language access & meaningful two-way communication |  |  | CLAS Standards: advancing health & racial equity, through data collection, and diversifying workforce to represent community; ensuring language access & meaningful two-way communication
Charles River Public Health District | Performance Standards |  | Develop standardized protocols for case investigations, outlining clear steps for immediate disease acknowledgment within 48 hours and routine disease acknowledgment within 7 days. | [7 empty] | Regional Public Health Nurse | Kerry Dunnell | 2025-01-01 | 2025-06-30 | Not Started |  | Regional Public Health Nurse first day was October 21, 2024. Following onboarding and training, this work is priority.
Charles River Public Health District | Performance Standards |  | Assess staffing and workload to allocate resources effectively for infectious disease investigations and epidemiology, adjusting staffing models as needed for sustainability and ensuring coverage with backup staff when necessary. | [7 empty] | Regional Public Health Nurse | Kerry Dunnell | 2024-12-01 | 2025-06-30 | Not Started |  | Regional Public Health Nurse first day was October 21, 2024. Following onboarding and training, this work is priority.
Charles River Public Health District | Performance Standards |  | Establish mechanisms for ongoing monitoring and evaluation of infectious disease case investigation activities and epidemiological trends to maintain high standards of quality and efficiency, identifying and addressing areas for improvement as necessary. | [6 empty] | TRUE | Regional Public Health Nurse | Kerry Dunnell | 2024-10-01 | 2025-06-30 | Not Started |  | Regional Public Health Nurse first day was October 21, 2024. Following onboarding and training, this work is priority.
Charles River Public Health District | Performance Standards |  | Create a comprehensive resource hub on infectious disease case investigation procedures, including proper documentation, communication protocols, and epidemiological data reporting requirements. | TRUE | [5 empty] | TRUE | Regional Public Health Nurse | Kerry Dunnell | 2024-12-01 | 2025-06-30 | Not Started |  | Regional Public Health Nurse first day was October 21, 2024. Following onboarding and training, this work is priority. Currently exploring whether this can be a collaborative activity with other shared services arrangements in our Training Hub region.
Charles River Public Health District | Performance Standards | Performance Standards 3 | 3 - Facilitate targeted training opportunities for staff members to address gaps in meeting the Performance Standards Standards for Local Public Health. |  | Self Assessment
Charles River Public Health District | Performance Standards | Performance Standards Topic Area | Tobacco Use Prevention |  |  |  | Tobacco Use Prevention
Charles River Public Health District | Performance Standards | Performance Standards Racial Equity Consideration | CLAS Standards: advancing health & racial equity, through data collection, and diversifying workforce to represent community; ensuring language access & meaningful two-way communication |  |  | CLAS Standards: advancing health & racial equity, through data collection, and diversifying workforce to represent community; ensuring language access & meaningful two-way communication
Charles River Public Health District | Performance Standards |  | Utilize tools such as the SSA Capacity Assessment Results Toolkit (CART) and Performance Standards Self-Assessment Tool and Addendum to identify areas for improvement within the SSA | [7 empty] | Regional Environmental Health Agent | Sam Menard | 2024-09-01 | 2024-12-30 | In Progress |  | All communities are completing the Self-Assessment tool with assistance from Regional Health Inspector
Charles River Public Health District | Performance Standards |  | Seek out training resources, such as TRAIN MA, to ensure all necessary staff members complete relevant trainings addressing identified gaps in meeting the Performance Standards within the SSA. | [7 empty] | Sam Menard | Regional Environmental Health Agent | 2024-10-01 | 2025-06-30 | In Progress |  | On going. Charles River PHD staff discuss potential training needs and opportunities at regular staff meetings.
Charles River Public Health District | Performance Standards |  | Create and utilize a system to gather input from staff members on the effectiveness and relevance of completed training sessions, utilizing this feedback to improve the selection of future training opportunities. | [7 empty] | Sam Menard | Regional Environmental Health Agent | 2025-01-01 | 2025-02-28 | Not Started |  | A system to gather feedback on training opportunities will be developed.
Charles River Public Health District | Performance Standards |  | Encourage cross-training and tagalong inspections among SSA member municipalities. | [7 empty] | Sam Menard | Regional Environmental Health Agent | 2024-07-01 | 2025-06-30 | In Progress |  | Ongoing. Charles River PHD staff and communities have each requested opportunities for tagalong & cross training. CRPHD staff provide a monthly summary of numbers of activities in each community.
Charles River Public Health District | Elective | Elective 1 | 7- Education, Training, and Credentialing: Assess and plan for all staff to work towards meeting the Workforce Standards
Charles River Public Health District | Elective | Elective Racial Equity Consideration | Workforce Diversity: create a work culture of diversity, equity, inclusion, and belonging, that values different viewpoints and lived experiences to improve employee satisfaction & retention |  |  | Workforce Diversity: create a work culture of diversity, equity, inclusion, and belonging, that values different viewpoints and lived experiences to improve employee satisfaction & retention
Charles River Public Health District | Elective |  | Document all current municipal and shared staff’s progress in completing all appropriate/required trainings in alignment with the Workforce Standards for Local Public Health. | [7 empty] | Regional Environmental Health Inspector | Sam Menard | 2024-09-01 | 2025-02-28 | Stalled |  | Pending completion of Self Assessment Tool. A spreadsheet of all staff in shared services and community has been created and will be populated with requirements during TriTerm2. A meeting with the Advisory Board in TriTerm2 will include a presentation from the Training Hub and review of specific training needs.
Charles River Public Health District | Elective |  | Ensure all staff within the SSA have completed ICS100/NIMS 700 and for those with a leadership role, ICS 200. | [7 empty] | Regional Environmental Health Inspector | Administrative Specialist | 2024-10-01 | 2025-02-28 | Stalled |  | Pending completion of Self Assessment Tool. A spreadsheet of all staff in shared services and community has been created and will be populated with requirements during TriTerm2. A meeting with the Advisory Board in TriTerm2 will include a presentation from the Training Hub and review of specific training needs.
Charles River Public Health District | Elective |  | Ensure staff who have worked for local or state public health for at least 7 years, but who do not meet these requirements, request a Workforce Development Standards Waiver. | [7 empty] | Regional Environmental Health Inspector | Administrative Specialist | 2024-10-01 | 2025-02-28 | Stalled |  | Pending completion of Self Assessment Tool. A spreadsheet of all staff in shared services and community has been created and will be populated with requirements during TriTerm2. A meeting with the Advisory Board in TriTerm2 will include a presentation from the Training Hub and review of specific training needs.
Charles River Public Health District | Elective |  | Ensure all employees have an TRAIN MA account. | [7 empty] | Regional Environmental Health Inspector | Administrative Specialist | 2024-04-15 | 2025-06-30 | In Progress |  | All employees names and contact information were provided for initial upload into TRAIN. As new staff join either the collaborative or a community, each person is provided instructions for establishing a TRAIN account.
Charles River Public Health District | Elective |  | LPH and SSA prioritize integrating and completing Local Public Health Training Program Tier 1 Foundational Knowledge TRAIN MA, Tier 2 Local Public Health Intensive Training and Tier 3 Applied Practice Local Public Health Training Hub into onboarding plans for all new hires. | [7 empty] | Kerry Dunnell | Sam Menard | 2024-10-01 | 2025-06-30 | In Progress |  | Information about training requirements for each role has been provided to each community. A spreadsheet of all staff in shared services and community has been created and will be populated with requirements during TriTerm2. A meeting with the Advisory Board in TriTerm2 will include a presentation from the Training Hub and review of specific training needs.

## Comments
Row 27 | can we change dates and assigned staff? | Kerry Dunnell | 11/17/24 3:50 PM

## Summary
Dark Blue | Locked Rows
Light Blue | SSA Data Entry Fields
Yellow | Pre-filled text from workplans/budgets
Grey | Intentionally blank space/hidden columns
White | Consistent text across all workplans
Red | PC Data Entry only