## Melrose Workplan Tracker FY2026
Modified By | Modified | SSA (Hidden) | Label (Hidden) | Objectives | Description (pre-filled) | Activity | Objective Drop Down | Performance Measure | Racial Equity Theme | Racial Equity Activity | This objective was selected due to | Performance Standards Topic Area | Environmental Health Subcategory (if applicable) | SSC Contact | PC Contact | Selected Activity | Staff Lead | Support Staff | Start Date | End Date | T1 Status | T1 Progress Notes | T2 Status | T2 Progress Notes | T3 Status | T3 Progress Notes
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | [11 empty] | SSC Email | PC Email | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Grant Administration | Grant Administration | PHE Grant Requirement 1: Grant Administration: Complete/perform all PHE Grant Program contractual requirements for the upcoming fiscal year | [10 empty] | .
dwu@cityofmelrose.org | 2025-06-05 09:48 | SSA Name | Grant Administration |  |  | A. Attend monthly PHE Grantee meetings – ensure attendance of lead municipality and Shared Services Coordinator (SSC), or a designated alternate. | [9 empty] | . | Deanna Wu | achui@cityofmelrose.org | 2025-07-01 | 2026-06-30
dwu@cityofmelrose.org | 2025-06-05 09:48 | SSA Name | Grant Administration |  |  | B. Maintain Letters of Commitment (LOC) from all Participating Municipalities in the SSA. | [9 empty] | . | Deanna Wu | achui@cityofmelrose.org | 2025-07-01 | 2026-06-30
dwu@cityofmelrose.org | 2025-06-05 09:51 | SSA Name | Grant Administration |  |  | C. Complete and submit PHE triannual reports in collaboration with your Shared Services Coordinator and all municipalities within the SSA. | [9 empty] | . | Deanna Wu | Gruha Patel | 2025-07-01 | 2026-06-30
dwu@cityofmelrose.org | 2025-06-05 09:48 | SSA Name | Grant Administration |  |  | D. Governing bodies established through the Intermunicipal Agreement (IMA) shall meet a minimum of once per quarter. | [9 empty] | . | Deanna Wu | achui@cityofmelrose.org | 2025-07-01 | 2026-06-30 |  | Enter date(s) of governing body's meeting(s). |  | Enter date(s) of governing body's meeting(s). |  | Enter date(s) of governing body's meeting(s).
dwu@cityofmelrose.org | 2025-06-05 09:51 | SSA Name | Grant Administration |  |  | E. Send annual notification to all Participating Municipalities no later than October 31st of each grant year. Such notification shall be substantially consistent with Attachment 1 of the PHE Engagement Scope in terms of required language and addressee list. Proof of notification shall be submitted to Program Coordinator no later than November 15th of each fiscal year. | [9 empty] | . | Deanna Wu | achui@cityofmelrose.org | 2025-07-01 | 2025-11-15
dwu@cityofmelrose.org | 2025-06-05 09:48 | SSA Name | Grant Administration |  |  | F. Ensure that all Participating Municipalities maintain 100% continuous MAVEN coverage which means that each Participating Municipality has an active, designated MAVEN user and back-up user. Back up user should be a person that has been trained to perform active case investigation and follow-up and could actively investigate a case of disease in their back up capacity. Preferably a public health nurse or regional epidemiologist. | [9 empty] | . | Gruha Patel | Deanna Wu | 2025-07-01 | 2026-06-30
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Governance | Governance | PHE Grant Requirement 2: Governance: Execute and maintain IMA or equivalent | [10 empty] | .
dwu@cityofmelrose.org | 2025-06-05 10:09 | SSA Name | Governance |  |  | A. Assess and update existing IMA or equivalent (e.g., Health District bylaws) for your SSA. | [9 empty] | . | Deanna Wu | achui@cityofmelrose.org | 2025-10-01 | 2026-01-30
dwu@cityofmelrose.org | 2025-06-05 09:54 | SSA Name | Governance |  |  | B. Review SSA services and responsibilities planned for FY26. If these services and/or responsibilities are not covered in the existing IMA or equivalent Scope of Services section or exhibit, request legal technical support or work with municipal attorney to address. | [9 empty] | . | Deanna Wu | achui@cityofmelrose.org | 2025-07-01 | 2025-09-30
dwu@cityofmelrose.org | 2025-06-05 09:13 | SSA Name | Governance |  |  | C. Review IMA or equivalent for expiration dates (if applicable) as well as annual review/ assessment requirements and perform accordingly. Request technical support or work with municipal attorney as needed to renew or amend. | [9 empty] | . | Deanna Wu | achui@cityofmelrose.org
dwu@cityofmelrose.org | 2025-06-05 10:09 | SSA Name | Governance |  |  | D. Submit revisions to the IMA or equivalent to your Program Coordinator within 30 calendar days of full execution. | [9 empty] | . | Deanna Wu | achui@cityofmelrose.org | 2026-02-02 | 2026-03-03
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | FPHS Review | FPHS Review | Foundational Public Health Services (FPHS) Review: Review and utilize the data from the FPHS Shared Services Review |  |  | Enter Custom Performance Measure | [7 empty] | .
dwu@cityofmelrose.org | 2025-06-05 10:09 | SSA Name | FPHS Review |  |  | A. Using template provided by OLRH, Shared Services Coordinator to email the FPHS Preliminary Results slide deck to all Participating Municipality Board of Health members and health directors who did not attend the SSAs 2025 preliminary results meeting with BME. (T1) | [9 empty] | . | Deanna Wu |  | 7/1/2025 | 10/31/25 | Complete | Completed on 5/29/2025.
dwu@cityofmelrose.org | 2025-06-12 13:02 | SSA Name | FPHS Review |  |  | B. In advance of governance board discussion, Shared Services Coordinator meet with a technical support provider to review results and prepare for the meeting. Work with the technical support provider to select at least one discussion topic from the FPHS Discussion Facilitation Guide. | [9 empty] | . | Deanna Wu | Gruha Patel | 7/1/2025 | 10/31/2025
dwu@cityofmelrose.org | 2025-06-12 13:02 | SSA Name | FPHS Review |  |  | C. Ensure that FPHS FY25 Report appears on the agenda and is discussed during at least one governance board meeting. Representative to facilitate discussion using the FPHS Discussion Facilitation Guide about increased capacity for partnerships, collaboration, or service sharing, both internal and external. | [9 empty] | . | Deanna Wu | achui@cityofmelrose.org | 7/1/2025 | 10/31/2025
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | SAPHE 2.0 Reporting | SAPHE 2.0 Reporting | Ensure each participating municipality (LPH Entity) completes the Annual SAPHE 2.0 reporting requirements |  |  | Enter Custom Performance Measure | [7 empty] | .
dwu@cityofmelrose.org | 2025-06-05 10:36 | SSA Name | SAPHE 2.0 Reporting |  |  | A. Shared Services Coordinator (SSC) and heads of participating municipalities to attend the annual SAPHE 2.0 reporting introductory webinar(s)/technical assistance meeting(s) (late 2025-early 2026 / T2) | [9 empty] | . | Deanna Wu | achui@cityofmelrose.org, Jen Murphy, Laura Vlasuk, MaryAnn O'Connor | 11/1/2025 | 2/28/2026
dwu@cityofmelrose.org | 2025-06-05 10:36 | SSA Name | SAPHE 2.0 Reporting |  |  | B. SSC to notify Participating Municipalities of SAPHE 2.0 reporting requirements (OLRH to provide template email). (Estimated T1/T2/T3) | [9 empty] | . | Deanna Wu | achui@cityofmelrose.org, Jen Murphy, Laura Vlasuk, MaryAnn O'Connor | 7/1/2025 | 10/31/2025
dwu@cityofmelrose.org | 2025-06-05 10:36 | SSA Name | SAPHE 2.0 Reporting |  |  | C. SSC or equivalent shall ensure SAPHE 2.0 reporting compliance of all participating municipalities (January - February 2026 / T2) | [9 empty] | . | Deanna Wu | achui@cityofmelrose.org, Jen Murphy, Laura Vlasuk, MaryAnn O'Connor | 11/1/2025 | 2/28/2026
dwu@cityofmelrose.org | 2025-06-05 10:36 | SSA Name | SAPHE 2.0 Reporting |  |  | D. SSC to ensure that all PHE funded staff complete LPH Workforce Survey. SSC to support OLRH in encouraging local public health staff employed by participating municipalities to complete LPH Workforce Survey (Estimated T2) | [9 empty] | . | Deanna Wu | achui@cityofmelrose.org, Jen Murphy, Laura Vlasuk, MaryAnn O'Connor | 11/1/2025 | 2/28/2026
dwu@cityofmelrose.org | 2025-06-05 10:36 | SSA Name | SAPHE 2.0 Reporting |  |  | E. Vendor shall ensure that Participating Municipalities fully onboard to METRIK and complete inspections for available modules (e.g., Food Inspections, Bathing Beaches, Lab Results, Housing, etc.) in FY26, OR upload documents following instructions from OLRH to complete the document review process. (Estimated T3) | [9 empty] | . | Deanna Wu | achui@cityofmelrose.org, Jen Murphy, Laura Vlasuk, MaryAnn O'Connor | 3/1/2026 | 6/30/2026
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | METRIK | METRIK | Participate in the onboarding process to METRIK |  |  | Enter Custom Performance Measure | [7 empty] | .
dwu@cityofmelrose.org | 2025-06-05 10:36 | SSA Name | METRIK |  |  | A. If inspectional software costs are currently paid through PHE Grant funds and your municipality will not be assuming this expense, work with relevant groups (e.g., municipal IT staff, health department staff, administrators, etc.) to retire existing inspectional systems/software in coordination with METRIK team recommendations. In coordination with relevant groups, begin planning for the offboarding of existing inspectional software. This includes but is not limited to data migration, license closure, and internal staff communication, in alignment with METRIK guidance. | [9 empty] | . | Deanna Wu | achui@cityofmelrose.org, Jen Murphy, Laura Vlasuk, MaryAnn O'Connor | TBD | TBD
dwu@cityofmelrose.org | 2025-06-05 10:36 | SSA Name | METRIK |  |  | B. Facilitate conversations with key municipal contacts (e.g., such as public health directors, department heads, SSCs, and IT leads, etc.) using guidance from the METRIK team, to understand and confirm each municipality’s adoption plans for METRIK. Separately, support onboarding by assisting key municipal contacts with the timely submission of required documentation for user provisioning. Escalate any concerns or delays with meeting submission deadlines as needed. | [9 empty] | . | achui@cityofmelrose.org, Jen Murphy, Laura Vlasuk, MaryAnn O'Connor | Deanna Wu | TBD | TBD
dwu@cityofmelrose.org | 2025-06-05 10:39 | SSA Name | METRIK |  |  | C. Coordinate with key municipal contacts to ensure that all PHE-funded staff attend required METRIK trainings. Encourage participation from additional relevant groups (e.g., municipal IT staff, health department staff, administrators, etc.) to ensure comprehensive onboarding and effective system use. Municipalities should designate a training coordinator to track participation and ensure completion is documented to DPH. | [9 empty] | . | Deanna Wu | Gruha Patel | TBD | TBD
dwu@cityofmelrose.org | 2025-06-17 11:20 | SSA Name | Sustainability 1 | Sustainability 1 | Communication & Engagement: Raise awareness of shared services and impact to local resident and communities |  | Sustainability 1 | Enter Custom Performance Measure | Community Engagement: partner with community-based organizations, extending reach to historically under-resourced populations & enhancing FPHS delivery capabilities | Cultivate municipal support and buy-in from stakeholder groups (prioritizing municipal stakeholders, like health department staff and municipal leadership) | [5 empty] | .
dwu@cityofmelrose.org | 2025-06-12 13:26 | SSA Name | Sustainability 1 | Sustainability Racial Equity Theme | Community Engagement: partner with community-based organizations, extending reach to historically under-resourced populations & enhancing FPHS delivery capabilities | [10 empty] | .
dwu@cityofmelrose.org | 2025-06-17 11:20 | SSA Name | Sustainability 1 | Sustainability Racial Equity Activity |  | Cultivate municipal support and buy-in from stakeholder groups (prioritizing municipal stakeholders, like health department staff and municipal leadership) | [9 empty] | .
dwu@cityofmelrose.org | 2025-06-12 13:10 | SSA Name | Sustainability 1 |  |  | A. Improve awareness of your shared service arrangement and services provided to key partners in your communities (e.g., LBOHs, Select Boards, Finance Committees, Town Administrators/Managers/Mayors, local legislators, nonprofits, coalitions, and other community partners). Consider use of newsletters, press releases, articles, presentations at public meetings, and quarterly memos targeted for appropriate audience(s) showing value and benefits of shared services. | [9 empty] | TRUE | Deanna Wu | achui@cityofmelrose.org, Jen Murphy, Laura Vlasuk, MaryAnn O'Connor | 2025-10-01 | 2026-06-30
dwu@cityofmelrose.org | 2025-06-12 13:10 | SSA Name | Sustainability 1 |  |  | B. Prepare monthly and/or quarterly activity reports, showing delivery of shared services to each Participating Municipality. Circulate to appropriate audiences to advance awareness of the SSA and benefits to local residents and communities. | [9 empty] | TRUE | Gruha Patel | Deanna Wu | 2025-10-01 | 2026-06-30
dwu@cityofmelrose.org | 2025-06-17 12:40 | SSA Name | Sustainability 1 |  |  | C. Prepare an annual report of SSA activities and delivery of shared services (inspections, enforcement actions, etc.). Consider distributing these materials strategically during the annual budget cycle, to advance support of funding to local public health. | [9 empty] | TRUE | Deanna Wu, Gruha Patel | achui@cityofmelrose.org, Jen Murphy, Laura Vlasuk, MaryAnn O'Connor | 2025-09-01 | 2025-12-31
dwu@cityofmelrose.org | 2025-06-12 13:10 | SSA Name | Sustainability 1
dwu@cityofmelrose.org | 2025-06-12 13:10 | SSA Name | Sustainability 1
dwu@cityofmelrose.org | 2025-06-12 13:10 | SSA Name | Sustainability 1
dwu@cityofmelrose.org | 2025-06-12 13:10 | SSA Name | Sustainability 1
dwu@cityofmelrose.org | 2025-06-12 13:10 | SSA Name | Sustainability 1
dwu@cityofmelrose.org | 2025-06-12 13:10 | SSA Name | Sustainability 1
dwu@cityofmelrose.org | 2025-06-12 13:10 | SSA Name | Sustainability 1
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Sustainability Custom |  |  | Custom Activity Option
dwu@cityofmelrose.org | 2025-06-12 13:39 | SSA Name | Sustainability 3 | Sustainability 2 | Expanded Sharing of Internal Services: Explore opportunities for expanded sharing of services |  | Sustainability 3 | Enter Custom Performance Measure | Environmental Justice: Allocate resources equitably to close gaps in environmental protections and access. | Prioritize support to communities with EJ BG | [5 empty] | .
dwu@cityofmelrose.org | 2025-06-12 13:39 | SSA Name | Sustainability 3 | Sustainability Racial Equity Theme | Environmental Justice: Allocate resources equitably to close gaps in environmental protections and access. | [10 empty] | .
dwu@cityofmelrose.org | 2025-06-12 13:39 | SSA Name | Sustainability 3 | Sustainability Racial Equity Activity |  | Prioritize support to communities with EJ BG | [9 empty] | .
dwu@cityofmelrose.org | 2025-06-12 13:39 | SSA Name | Sustainability 3 |  |  | A. Utilizing FPHS Shared Services Review Results, review shared staff capacity and expertise in FPHS Service Delivery Tool to identify strengths and areas of improvement. | [9 empty] | TRUE | Gruha Patel | Deanna Wu | 2025-07-01 | 2025-12-31
dwu@cityofmelrose.org | 2025-06-12 13:39 | SSA Name | Sustainability 3 |  |  | B. Assess the level of shared service adoption of each Participating Municipality and identify opportunities for improved sharing of services. Identify and address barriers to sharing services if applicable. | [9 empty] | TRUE | Deanna Wu | Gruha Patel | 2025-07-01 | 2026-06-30
dwu@cityofmelrose.org | 2025-06-12 13:39 | SSA Name | Sustainability 3 |  |  | C. Identify municipal staff capacity to support SSA through training (e.g. mentoring, shadowing opportunities), back-up support, and limited inspectional capacity or other support. | [9 empty] | TRUE | Deanna Wu | achui@cityofmelrose.org, Jen Murphy, Laura Vlasuk, MaryAnn O'Connor | 2025-07-01 | 2026-06-30
dwu@cityofmelrose.org | 2025-06-12 13:39 | SSA Name | Sustainability 3 |  |  | D. Consider sharing of services beyond existing PHE funded shared staff. Develop a request process for Participating Municipalities and appropriate municipal or regional Standard Operating Procedures.
dwu@cityofmelrose.org | 2025-06-12 13:39 | SSA Name | Sustainability 3 |  |  | E. Develop standard operating procedures, activities, and fees across Participating Municipalities to ensure consistency and equity in service delivery.
dwu@cityofmelrose.org | 2025-06-12 13:39 | SSA Name | Sustainability 3 |  |  | F. If applicable, request Legal TA through OLRH to review expanded sharing of resources.
dwu@cityofmelrose.org | 2025-06-12 13:39 | SSA Name | Sustainability 3 |  |  | G. Engage with Participating Municipalities Boards of Health to approve proposed standard operating procedures, activities, and fees across municipalities to ensure consistency and equity in service delivery.
dwu@cityofmelrose.org | 2025-06-12 13:39 | SSA Name | Sustainability 3 |  |  | H. [Applicable for SSAs that have municipalities with Inspectional Services Department (ISD)] Collaborate with the Inspectional Services Department (ISD) to discuss sharing existing resources in areas where staffing is needed for the SSA.
dwu@cityofmelrose.org | 2025-06-12 13:39 | SSA Name | Sustainability 3 |  |  | I. Work to adopt regional uniform local regulations (such as septic, private well, environmental review, and outside consultant regs) to create a level playing field and cohesive regulatory program that better justifies having an SSA-wide fee schedule.
dwu@cityofmelrose.org | 2025-06-12 13:39 | SSA Name | Sustainability 3 |  |  | J. Consider offering additional services at the SSA level, such as Certified Public Water Supply Operator, Licensed Site Professional, and Certified Wastewater Treatment Plant Operator, to Towns within the SSA that are having staffing issues with finding qualified and credentialed part-time employees to fill these roles.
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Sustainability Custom |  |  | Custom Activity Option
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Sustainability Objective | Sustainability 3 (optional) |  |  | Select Sustainability Objective | Enter Custom Performance Measure | Select Equity Theme | Enter Racial Equity Activity | [5 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Sustainability Objective | Sustainability Racial Equity Theme | Select Equity Theme | [10 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Sustainability Objective | Sustainability Racial Equity Activity |  | Enter Racial Equity Activity | [9 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Sustainability Objective
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Sustainability Objective
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Sustainability Objective
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Sustainability Objective
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Sustainability Objective
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Sustainability Objective
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Sustainability Objective
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Sustainability Objective
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Sustainability Objective
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Sustainability Objective
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Sustainability Custom |  |  | Custom Activity Option
dwu@cityofmelrose.org | 2025-06-17 12:58 | SSA Name | Performance Standards 3 | Performance Standards 1 | Facilitate targeted training opportunities for staff members to address gaps in meeting the Performance Standards |  | Performance Standards 3 | Enter Custom Performance Measure | Workforce Diversity: Cultivate a work culture of diversity and belonging, that values different viewpoints and lived experiences to improve employee satisfaction & retention | Develop systems for providing support and mentorship during the workday for employees. | Self Assessment | Environmental Health | Food Protection |  |  | .
dwu@cityofmelrose.org | 2025-06-12 13:39 | SSA Name | Performance Standards 3 | Performance Standards Topic Area | Environmental HealthFood Protection | [10 empty] | .
dwu@cityofmelrose.org | 2025-06-17 12:55 | SSA Name | Performance Standards 3 | Performance Standards Racial Equity Theme | Workforce Diversity: Cultivate a work culture of diversity and belonging, that values different viewpoints and lived experiences to improve employee satisfaction & retention | [10 empty] | .
dwu@cityofmelrose.org | 2025-06-17 12:58 | SSA Name | Performance Standards 3 | Performance Standards Racial Equity Activity |  | Develop systems for providing support and mentorship during the workday for employees. | [9 empty] | .
dwu@cityofmelrose.org | 2025-06-17 13:16 | SSA Name | Performance Standards 3 |  |  | A. Utilize tools such as the SSA Capacity Assessment Results Toolkit (CART) and Performance Standards Self-Assessment Tool and Addendum to identify areas for improvement within the SSA concerning [insert PS category/subcategory]. | [9 empty] | TRUE | Gruha Patel | Deanna Wu | 2025-07-01 | 2025-12-31
dwu@cityofmelrose.org | 2025-06-17 13:16 | SSA Name | Performance Standards 3 |  |  | B. Seek out training resources, such as TRAIN MA, to ensure all necessary staff members complete relevant trainings addressing identified gaps in meeting the Performance Standards within the SSA. | [9 empty] | TRUE | Deanna Wu | achui@cityofmelrose.org, Jen Murphy, Laura Vlasuk, MaryAnn O'Connor, Skyler Lesser-Roy, Steve Casey, Terry Kennedy | 2025-07-01 | 2026-06-30
dwu@cityofmelrose.org | 2025-06-12 13:39 | SSA Name | Performance Standards 3 |  |  | C. Create and utilize a system to gather input from staff members on the effectiveness and relevance of completed training sessions, utilizing this feedback to improve the selection of future training opportunities.
dwu@cityofmelrose.org | 2025-06-12 13:49 | SSA Name | Performance Standards 3 |  |  | D. Work with the Training Hubs and/or coordinate tagalong inspections for knowledge sharing with all Participating Municipalities. | [9 empty] | TRUE | Dan Thompson | Deanna Wu, Skyler Lesser-Roy, Steve Casey, Terry Kennedy | 2025-07-01 | 2026-06-30
dwu@cityofmelrose.org | 2025-06-12 13:39 | SSA Name | Performance Standards 3
dwu@cityofmelrose.org | 2025-06-12 13:39 | SSA Name | Performance Standards 3
dwu@cityofmelrose.org | 2025-06-12 13:39 | SSA Name | Performance Standards 3
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Performance Standards Custom |  |  | Custom Activity Option
dwu@cityofmelrose.org | 2025-06-17 13:01 | SSA Name | Performance Standards 4 | Performance Standards 2 | Disease Control and Prevention: Ensure adherence to infectious disease case investigation requirements, while enhancing staff training, capacity, and quality improvement initiatives |  | Performance Standards 4 | Enter Custom Performance Measure | Workforce Diversity: Cultivate a work culture of diversity and belonging, that values different viewpoints and lived experiences to improve employee satisfaction & retention | Develop systems for providing support and mentorship during the workday for employees. | Foundational Public Health Services Review | Disease Control and Prevention |  |  |  | .
dwu@cityofmelrose.org | 2025-06-17 13:01 | SSA Name | Performance Standards 4 | Performance Standards Topic Area | Disease Control and Prevention | [10 empty] | .
dwu@cityofmelrose.org | 2025-06-17 13:01 | SSA Name | Performance Standards 4 | Performance Standards Racial Equity Theme | Workforce Diversity: Cultivate a work culture of diversity and belonging, that values different viewpoints and lived experiences to improve employee satisfaction & retention | [10 empty] | .
dwu@cityofmelrose.org | 2025-06-17 13:01 | SSA Name | Performance Standards 4 | Performance Standards Racial Equity Activity |  | Develop systems for providing support and mentorship during the workday for employees. | [9 empty] | .
dwu@cityofmelrose.org | 2025-06-17 13:16 | SSA Name | Performance Standards 4 |  |  | A. Assess FPHS Shared Service Review Preliminary Results to identify any gaps in Assessment & Surveillance Foundational Capability service delivery and understand staff capacity and expertise | [9 empty] | TRUE | Gruha Patel | Deanna Wu | 2025-07-01 | 2025-12-31
dwu@cityofmelrose.org | 2025-06-17 13:16 | SSA Name | Performance Standards 4 |  |  | B. Assess staffing and workload across SSA to allocate resources effectively for infectious disease investigations and epidemiology, work within SSA to adjust staff sharing as needed for sustainability and ensure MAVEN coverage with backup staff when necessary. | [9 empty] | TRUE | Deanna Wu | achui@cityofmelrose.org, Gruha Patel, Heidi Gerostergios, Jen Murphy, kdacampo@winchester.us, Laura Vlasuk, MaryAnn O'Connor, Melissa Lowry, mtamagna@cityofmalden.org, sbrown@wakefield.ma.us | 2025-07-01 | 2026-06-30
dwu@cityofmelrose.org | 2025-06-17 13:18 | SSA Name | Performance Standards 4 |  |  | C. Connect with local public health nurse consultants to understand local resources and processes for communicable disease response | [9 empty] | TRUE | chassearobin@umass.edu, Deanna Wu, Gruha Patel | Heidi Gerostergios, kdacampo@winchester.us, Melissa Lowry, mtamagna@cityofmalden.org, sbrown@wakefield.ma.us | 2025-07-01 | 2025-12-31
dwu@cityofmelrose.org | 2025-06-12 13:49 | SSA Name | Performance Standards 4 |  |  | D. Develop standardized protocols for coordination between local public health nurse and/or epidemiologist to respond to case investigations, outlining clear steps for immediate disease acknowledgment within 48 hours and routine disease acknowledgment within 7 days in MAVEN.
dwu@cityofmelrose.org | 2025-06-12 13:49 | SSA Name | Performance Standards 4 |  |  | E. Ensure understanding and use of MAVEN comprehensive training and resource hub on infectious disease case investigation procedures, including proper documentation, communication protocols, and epidemiological data reporting requirements.
dwu@cityofmelrose.org | 2025-06-17 13:18 | SSA Name | Performance Standards 4 |  |  | F. Establish mechanisms for ongoing monitoring and evaluation of infectious disease case investigation activities and epidemiological trends to maintain high standards of quality and efficiency, identifying and addressing areas for improvement as necessary. | [9 empty] | TRUE | Gruha Patel | achui@cityofmelrose.org, Deanna Wu, Heidi Gerostergios, Jen Murphy, kdacampo@winchester.us, Laura Vlasuk, MaryAnn O'Connor, Melissa Lowry, mtamagna@cityofmalden.org, sbrown@wakefield.ma.us | 2025-07-01 | 2026-06-30
dwu@cityofmelrose.org | 2025-06-12 13:49 | SSA Name | Performance Standards 4
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Performance Standards Custom |  |  | Custom Activity Option
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Performance Standards Objective | Performance Standards 3 (optional) |  |  | Select Performance Standards Objective | Enter Custom Performance Measure | Select Equity Theme | Enter Racial Equity Activity | Select Option | Select Topic Area |  |  |  | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Performance Standards Objective | Performance Standards Topic Area | Select Topic Area | [10 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Performance Standards Objective | Performance Standards Racial Equity Theme | Select Equity Theme | [10 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Performance Standards Objective | Performance Standards Racial Equity Activity |  | Enter Racial Equity Activity | [9 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Performance Standards Objective
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Performance Standards Objective
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Performance Standards Objective
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Performance Standards Objective
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Performance Standards Objective
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Performance Standards Objective
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Performance Standards Objective
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Performance Standards Custom |  |  | Custom Activity Option
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | Elective 1 (optional) |  |  | Select Elective Objective | Enter Custom Performance Measure | Select Equity Theme | Enter Racial Equity Activity | Select Option |  |  |  |  | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | Elective Racial Equity Theme | Select Equity Theme | [10 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | Elective Racial Equity Activity |  | Enter Racial Equity Activity | [9 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | ..
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Custom Elective Objective |  |  | Custom Activity Option | [9 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | Elective 2 (optional) |  |  | Select Elective Objective | Enter Custom Performance Measure | Select Equity Theme | Enter Racial Equity Activity | Select Option |  |  |  |  | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | Elective Racial Equity Theme | Select Equity Theme | [10 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | Elective Racial Equity Activity |  | Enter Racial Equity Activity | [9 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Custom Elective Objective |  |  | Custom Activity Option | [9 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | Elective 3 (optional) |  |  | Select Elective Objective | Enter Custom Performance Measure | Select Equity Theme | Enter Racial Equity Activity | Select Option |  |  |  |  | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | Elective Racial Equity Theme | Select Equity Theme | [10 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | Elective Racial Equity Activity |  | Enter Racial Equity Activity | [9 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Select Elective Objective | [12 empty] | .
jmetri@bmestrategies.com | 2025-05-24 15:31 | SSA Name | Custom Elective Objective |  |  | Custom Activity Option | [9 empty] | .

## Comments
Sheet | @kristin.e.black@mass.gov @diana.c.acosta@mass.gov activity tracker updated and available for your review/testing (light blue is for SSA data entry, grey columns will be hidden) | Christina Moore | 05/13/25 11:09 AM

## Summary
Dark Blue | Locked Rows
Light Blue | SSA Data Entry Fields
Grey | Intentionally blank space/hidden columns
White | Consistent text across all workplans